## Week 1
Date | Task Name | Time Started | Description | Estimated Time | Time (minutes) | Time accuracy | Total (minutes) | Total (Hours)
2019-03-27 | AI | 9:30 | Started making the AI for the shoot em up part of the game. | 180 | 120 | 150 | 510 | 8.5
2019-03-29 | Unity 5 | 8PM | Watched a video on the new Unity tool | 30 | 30 | 100
2019-03-29 | Respond Effect | 9PM | Added a sound effect when the character responds. | 60 | 90 | 66.6667
2019-03-29 | Enemy | 11:15 | Fixed an issue where the enemy doesn't follow the play once he responds. Also worked on making the enemy take damage. | 120 | 180 | 66.6667
2019-04-04 | Shooting | 11:50 | Worked on shooting effects | 60 | 90 | 66.6667